## Fee Breakdown
		Approach (A)		Approach (B)		Approach (C)		Estimated Duration
%	Phase	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs	Not-To-Exceed	Rough % of Const. Costs
5.00%	Phase 1: / Programming	0.4%	$1,050	0.4%	$1,200	0.5%	$1,350	1.0 wks
20.00%	Phase 2: / Schematic Design	1.4%	$4,200	1.6%	$4,800	1.8%	$5,400	4.0 wks
20.00%	Phase 3: / Design Development	1.4%	$4,200	1.6%	$4,800	1.8%	$5,400	4.0 wks
30.00%	Phase 4: / Construction Documents	2.1%	$6,300	2.4%	$7,200	2.7%	$8,100	6.0 wks
5.00%	Phase 5: / Bidding & Contract Negotiation	0.4%	$1,050	0.4%	$1,200	0.5%	$1,350	1.0 wks
20.00%	Phase 6: / Construction Administration	1.4%	$4,200	1.6%	$4,800	1.8%	$5,400	n/a
100.00%	All Phases	7.0%	$21,000	8.0%	$24,000	9.0%	$27,000
Assuming a Construction Cost =								$300,000

## Hour Breakdown
Square Footage	2,000 SF
Estimated Dollar per Square Footage	150 $/SF
Total Estimated Construction Costs	$300,000.00
Architecture/Eng Fees - Percentage of Construction	7.0%
Architecture & Engineering Fees	$21,000.00

Average ($/Hr) Billing Rate	$55.00
		Each Phase	Cumulative	Hours dedicated to each phase	weeks - 1/2 person	weeks - 3/4 person	weeks - 1 person	weeks - 1.5 person	weeks - 2 people
Phase 1 - Programming	5.00%	$1,050.00	$1,050.00	19 hrs	1.0 wks	0.6 wks	0.5 wks	0.3 wks	0.2 wks
Phase 2 - Schematic	20.00%	$4,200.00	$5,250.00	76 hrs	3.8 wks	2.5 wks	1.9 wks	1.3 wks	1.0 wks
Phase 3 - Design Development	20.00%	$4,200.00	$9,450.00	76 hrs	3.8 wks	2.5 wks	1.9 wks	1.3 wks	1.0 wks
Phase 4 - Construction Documents	30.00%	$6,300.00	$15,750.00	115 hrs	5.7 wks	3.8 wks	2.9 wks	1.9 wks	1.4 wks
Phase 5 - Bidding and Construction Contract Negotiation	5.00%	$1,050.00	$16,800.00	19 hrs	1.0 wks	0.6 wks	0.5 wks	0.3 wks	0.2 wks
Phase 6 - Construction Administration	20.00%	$4,200.00	$21,000.00	76 hrs	3.8 wks	2.5 wks	1.9 wks	1.3 wks	1.0 wks
	100.00%	$21,000.00	$21,000.00	382 hrs	19.1 wks	12.7 wks	9.5 wks	6.4 wks	4.8 wks

Architecture Fees	65.00%	4.6%	$13,650.00
Civil Fees	8.00%	0.6%	$1,680.00
Structural Fees	10.00%	0.7%	$2,100.00
MEP Fees	12.00%	0.8%	$2,520.00
Other Consultants	5.00%	0.4%	$1,050.00
	100.00%	7.00%	$21,000.00

## Hourly Rates
Discipline	Approach / (A)	Approach / (B)	Approach / (C)	A Rough Estimated Percentage of Fees	A Rough Estimated Percentage of Overall Construction Costs
Architecture				73.00%	5.11%	$15,330.00
Level 1	$75/HR	$85/HR	$95/HR
Level 2	$60/HR	$70/HR	$80/HR
Level 3	$50/HR	$60/HR	$70/HR
Civil Engineer				0.00%	0.00%	$0.00
Level 1	$125/HR	$135/HR	$145/HR
Level 2	$110/HR	$120/HR	$130/HR
Level 3	$100/HR	$110/HR	$120/HR
Structural Engineer				2.00%	0.14%	$420.00
Level 1	$150/HR	$160/HR	$170/HR
Level 2	$100/HR	$110/HR	$120/HR
Level 3	$90/HR	$100/HR	$110/HR
Mechanical Engineer				0.00%	0.00%	$0.00
Level 1	$150/HR	$160/HR	$170/HR
Level 2	$100/HR	$110/HR	$120/HR
Level 3	$90/HR	$100/HR	$110/HR
Electrical Engineer				10.00%	0.70%	$2,100.00
Level 1	$150/HR	$160/HR	$170/HR
Level 2	$100/HR	$110/HR	$120/HR
Level 3	$90/HR	$100/HR	$110/HR
Plumbing Engineer				10.00%	0.70%	$2,100.00
Level 1	$150/HR	$160/HR	$170/HR
Level 2	$100/HR	$110/HR	$120/HR
Level 3	$90/HR	$100/HR	$110/HR
Potential Additional Consultants				5.00%	0.35%	$1,050.00
• Lighting
• Door Hardware Consultant
• Construction Specification Consultant
TOTAL				100.00%	7.00%	$21,000.00